## Sheet1
Instructions
Each member on the team needs to declare the work they have done the past week in this document. Information here will be deemed as accurate and validated by all members on the team. For each field filled wrongly, a grade penalty will be applied to the submission. For the "Work done the past week", work done falls into two categories. "Integrated" means that the task is already functioning with the rest of the project. "Not-integrated" means that the task is completed but is not working with the rest of the project. For the "Hours spent", please use whole numbers for the total amount of hours spent working on the project the past week. Make sure that you do not mutate any of the excel cells. Just fill them with what is neccessary.
Rationale
It is important to consider a task to be completed ONLY after integration. Integrating functionality and code into a larger code base, having everything work together can seem tedious and administrative. The value of the product is always greater than the sum of its parts. The parts need to come together. Since you are just starting on your software development journey, work done that has yet to be integrated is acknowledged. However, there may be penalties given to those who do not have any work done integrated into the main project. Effort may have been put in, but it did not contribute to the project. Penalties will be given for those who do not do work. Be honest when filling this up. If you find yourself lagging behind or stuck, seek help.
Team Name | SMEG
Team Progress | On Time
Name | DigiPen E-mail | Work done the past week (Give a summary in point form) |  | Hours spent | Individual Progress
|  | Integrated | Not-Integrated
Yong Yip Han | y.yiphanedgar@digipen.edu | Mob Array Creation Mob Spawn Wave Cycle Basic Mob Movement towards player | Droping Items Upon mob kills Drawing Mobs with sprite instead of circle | 20 | On Time | Week 1
Tay Sen Chuan | t.senchuan@digipen.edu | Bullet Structure Setup Mouse Tracking for aiming Bullet shooting and collision |  | 8 | On Time
Mah Ming Qian Michael | m.mah@digipen.edu | Main Menu | options upgrades credits difficulty | 2 | On Time
Geoffrey Cho Jian Ming | g.cho@digipen.edu | Death Screen Upgrades Screen Player creation, functions and movement Camera to centralize player |  | 15 | On Time

## Progress
Status
Ahead
On Time
Days behind
1 Week behind
2 Weeks or more behind